## Sheet1
Risk Event | Probability | Impact | Category | Mitigation Plan | Response Plan
Delay in third-party components delivery | Moderate | High | Schedule | Plan for possible delays by adding buffer time to the project schedule | Continuously monitor third-party components' progress and adjust the project schedule if necessary
Technical issues during development | Moderate | High | Technical | Allocate additional resources or bring in external expertise if required | Establish a rapid response team to address technical issues as they arise and ensure they don't significantly impact the project timeline
Insufficient resources | Low | High | Resource | Hire additional staff or outsource tasks to a third-party vendor | Maintain close communication with the HR department to promptly address resource needs
Scope creep | Moderate | High | Scope | Define and communicate the project scope clearly at project kick-off | Implement a robust change management process to evaluate and approve scope changes, ensuring they align with project goals
Unavailability of key team members | Low | Moderate | Resource | Maintain regular communication with team members to identify any potential issues | Cross-train team members and establish contingency plans to ensure that critical roles can be temporarily filled